## Sheet1
Year | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2023 | 2023 | 2023 | 2023
Month | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | April | May | June | July
Number of months to complete action | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 1 | 2 | 3 | 4
QA office Initial contact with department
QA Office Notification Email to Department
Meeting/ Discussion
Resources / previous reports
QA Office compile core stats report
Full departmental meeting | bar: April
Meeting with student committee | bar: April
Appoint of SE committee and allocate tasks, decide on QC sem 1 or sem 2 | bar: April
Core stats report | bar: April
Gather evidence | bar: April to July
Compile SE Report | bar: April to September
Dept Chair SE Report approval | bar: October
SE Report submission to Dean | bar: November
Set site visit date | bar: May to June
Appoint Peer Review Panel | bar: May to June
Confirmation of Peer Review Panel | bar: June
Confirm site visit dates and activities | bar: June
Finalise travel and accommodation for Peer Review Panel | bar: June to July
Draft SE Report to QA Office for comment | bar: November
Dean's office sends SE Report to Peer Review Panel | bar: December
Pre-site visit Peer Review panel meeting | bar: December to January
Site visit | bar: January
Peer Review report submission to Dean | bar: February
Peer Review Report submission to QA database | bar: February
Dean's office sends Peer Review report submission to Departmental Chair | bar: February
Departmental chair submit response to Peer Review Report | bar: March
Deans submission to QC | bar: March
QC Meeting (Agenda closes) | bar: April
Submit documentation to repository | bar: April
EC(S) meeting | bar: June
Follow-up report submission to QC | bar: April
QC Meeting for Follow-up Report | bar: May to June
Follow-up Report serves at EC(S) | bar: July