# Deliverables and timeframe for a typical self-evalution

| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PREPARATION FOR SELF-EVALUATION |  | SELF-EVALUATION |  |  |  | PREPARATION FOR SITE VISIT |  |
| Main tasks (deliverables) are to: - decide on a suitable site visit date; - set up a self-evaluation committee; - identify internal and/or external benchmarks to be applied when making quality judgements. - nominate peer reviewers; - decide on the scope and focus(es) of the self-evaluation in terms of the themes and criteria; - draft a project plan for managing the self-evaluation process. |  | Main tasks (deliverables) are to: - convene the self-evaluation committee on a regular basis and establish working groups, as needed; - study the previous self-evaluation and peer review reports and draft a contextualised introduction to the self-evaluation report (SER); - collect and interpret the evidence (e.g. through student/ stakeholder surveys or focus groups), and analyse and include the core statistical information, where applicable; - conduct a self-evaluation by making judgements on the quality of e.g. outcomes and processes, and compiling an evidence portfolio on each theme and/or criterion; - collate the different sections of the self-evaluation report into a first draft of the Self-Evaluation Report; - circulate the first draft of the SER to all staff and include their feedback and further reflections; - finalise the SER and discuss the key findings with Dean/RC Head, for approval. |  |  |  | Main tasks (deliverables) are to: - Submit the final self-evaluation report via dean or RC head to peer review panel; - Liaise with peer review panel, staff, students and stakeholders to set up interview schedule for site visit; - Make the final travel and logistical arrangements in order to host the peer review panel, and process the honoraria payments. |  |